## Slide 1
Process Metrics Process metrics pay particular attention on enhancing the long term process of the team or organisation.
Project Metrics Project metrics describes the project characteristic and execution process.
    Number of software developer
    Staffing pattern over the life cycle of software
    Cost and schedule
    Productivity

## Slide 2: Software Measurement
A measurement is an manifestation of the size, quantity, amount or dimension of a particular attributes of a product or process.

## Slide 3: Need of Software Measurement
Imparting quality in the current product or process
Anticipate future qualities of the product or process
Enhance the quality of a product or process
Regulate the state of the project in relation to budget and schedule

## Slide 4: Classification of Software Measurement
There are 2 types of software measurement
Direct Measurement In direct measurement the product, process or thing is measured directly using standard scale.
  lines of code (LOC),
  execution speed,
  memory size,
  defects per reporting time period.

## Slide 5
Indirect Measurement In indirect measurement the quantity or quality to be measured is measured using related parameter i.e. by use of reference.
functionality
complexity
efficiency
reliability
maintainability

## Slide 6
There are 4 functions related to software metrics
Planning
Organizing
Controlling
Improving

## Slide 7: Characteristics of software Metrics
Quantitative: Metrics must possess quantitative nature. It means metrics can be expressed in values.
Understandable: Metric computation should be easily understood ,the method of computing metric should be clearly defined.
Applicability: Metrics should be applicable in the initial phases of development of the software.

## Slide 8
Repeatable: The metric values should be same when measured repeatedly and consistent in nature.
Economical: Computation of metric should be economical.
Language Independent: Metrics should not depend on any programming language.

## Slide 9: Project Metrics
Schedule Variance : Any difference between the scheduled completion of an activity and the actual completion is known as Schedule Variance.
Schedule variance = ((Actual calendar days – Planned calendar days) + Start variance)/ Planned calendar days x 100.
Effort Variance: Difference between the planned outlined effort and the effort required to actually undertake the task is called Effort variance.
Effort variance = (Actual Effort – Planned Effort)/ Planned Effort x 100.
Size Variance: Difference between the estimated size of the project and the actual size of the project (normally in KLOC or FP)
Size variance = (Actual size – Estimated size)/ Estimated size x 100.

## Slide 10
Requirement Stability Index: Provides visibility and understanding into the magnitude and impact of requirements changes.
RSI = 1- ((No of changed + No of deleted + No of added) / Total no of Initial requirements) x100

## Slide 11
Productivity (Project): It is a measure of output from a related process for a unit of input.
Project Productivity = Actual Project Size / Actual Effort spent for the project
Productivity (for test case preparation)
Productivity in test case preparation = Actual no of test cases/ actual effort spent on test case preparation
Productivity (for test case execution)
Productivity in test case execution = actual number of test cases / actual effort spend on testing.

## Slide 12
Productivity (defect detection)
Productivity in defect detection = Actual number of defects (review + testing) / actual effort spent on (review + testing)
Productivity (defect fixation)
Productivity in defect fixation = actual no of defects fixed/ actual effort spent on defect fixation

## Slide 13
Schedule variance for a phase: The deviation between planned and actual schedule for the phases within a project.
Schedule variance for a phase = (Actual Calendar days for a phase – Planned calendar days for a phase + Start variance for a phase)/ (Planned calendar days for a phase) x 100
Effort variance for a phase: The deviation between planned and actual effort for various phases within the project.
Effort variance for a phase = (Actual effort for a phase – planned effort for a phase)/ (planned effort for a phase) x 100

## Slide 14: Process Metrics
Cost of Quality: It is a measure in terms of money for the quality performance within an organization
Cost of quality = (review + testing + verification review + verification testing + QA + configuration management + measurement + training + rework review + rework testing)/ total effort x 100
Cost of poor Quality: It is the cost of implementing imperfect processes and products.
Cost of poor quality = rework effort/ total effort x 100

## Slide 15
Defect Density: It is the number of defects detected in the software during the development divided by the size of the software (typically in KLOC or FP)
Defect density for a project = Total number of defects/ project size in KLOC
Review Efficiency: defined as the efficiency in harnessing/ detecting review defects in the verification stage.
Review efficiency = (number of defects caught in review)/ total number of defects caught) x 100

## Slide 16
Testing Efficiency:
Testing efficiency = 1 – ((defects found in acceptance)/ total no of testing defects) x 100
Defect removal efficiency: Gives the efficiency with which defects were detected and minimum defects were filtered down to the customer.
Defect removal efficiency = (1 – (total defects caught by customer/ total no of defects)) x 100